## Server Kanmo (hidden)
Kanmo Server ( IDcloudhost )
Kanmo App | https://kanmo.uidesk.id/CRM/auth_login.aspx
IP Public : 103.59.94.79
IP Private : 10.71.10.193
Rdp :
Administrator / Uid35k32!
Kanmo DB
Ip Public : 103.59.94.243
IP Private : 10.71.10.202
Rdp :
Administrator / Uid35k32!
SQL credential :
sa / Uid35k32!J4y4J4y4
Voice Pbx
sip.uidesk.id
ext :
101010 - 101025
Password :
Uidesk123!

## SIP TRunk & IVR Kanmo
SME SIP Trunk | Test Sip trunk In / Out |  | Details
CODE : SME -02775 | IN | Out
Customer : PT. SMART MILENIUM EFFISIENSI - TEST CALL KANMO
USER NAME : 1309002
LAYANAN : SIP REGISTER |  |  | IN : nomor yg anda tuju tidak terdaftar
ANI NUMBER : 02130205601 | Failed | Failed | OUT : Maaf jumlah deposit anda tidak cukup untuk melanjutkan panggilan ini
FR SIP TRUNK
SIP Trunk 103.129.205.228
Ani Number '+622130049718 | Success | Success
IVR Kanmo menggunkan No telp FR - 02130049718
Tgl 19-01-2024 Create IVR untuk Agent Kanmo
Ring Group 601 anggota ext 101010 - 101015

## Timeline Projek
WBS | TASK | Contributor | PREDECESSOR | START | Correction 1 | Correction 2 | Correction 3 | END | DAYS | % DONE | WORK DAYS | Documentation
1 | Voice Call (EPIC) | [6 empty] | - |  |  | -
.1 | Inbound Call PSTN 1 | Rizky Yulian Wibisono, Yoan Theodore Jebar |  | 2024-01-10 | 01/17/2024 |  |  | 2024-01-30 | 21 | 0% | 15
.1 | Inbound Call PSTN 2 | Rizky Yulian Wibisono, Yoan Theodore Jebar |  | 2024-01-10 | 01/17/2024 |  |  | 2024-01-30 | 21 | 0% | 15
1 | CRM (Ticketing System)
.1 | Modul Customer | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Modul Master Data | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Data Group Name |  |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Data Type | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Data Category | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Data Meta | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Data Sub Category | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 | 01/17/2024 |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Data Channel Ticket | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Data Department Escalation Unit | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Data Priority Scale | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Data Activity |  |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Data AUX Reason | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Data Status Ticket | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Data Group Agent | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Data Brand Category | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Data Fullfillment | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Data Holidays | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Data Brand Name | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Data Max Handle | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Data Site | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Modul Transaksi | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 | 01/17/2024 |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Modul Eskalasi Ticket | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Modul Pengaturan SLA Ticket | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Modul Taskboard User | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Modul Knowledge Management | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Modul Notifikasi Email | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Modul Customer Journey | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Modul Reporting | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Modul Management User | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Modul Pengaturan Agent | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
1 | Channel Email
.1 | Backend Email | Rizky Yulian Wibisono, Yoan Theodore Jebar |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 80% | 15
.1 | Inbox Email | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
.1 | Outboux Email | Samsu Rizal, Nurmansyah Candra Sakti, Wanda |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
1 | Wallboard System
.1 | Modul Wallboard Inbound Call | Restu Ramdhika Wibowo, Yoan Theodore Jebar, Samsu Rizal, Nurmansyah Candra Sakti |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 0% | 15
1 | Bantu Dagang
.1 | Modul Integrasi Bantu Dagang dengan Marketplace | Ryan, Restu Ramdhika Wibowo |  | 2024-01-10 |  |  |  | 2024-01-30 | 21 | 100% | 15
1 | Integrasi Bantu Dagang
.1 | Integrasi antara Bantu Dagan dengan CRM Ticketing System | Restu Ramdhika Wibowo, Samsu Rizal, Nurmansyah Candra Sakti |  | 2024-01-10 | 01/17/2024 |  |  | 2024-01-30 | 21 | 0% | 15
.1 | Integrasi Profiling Customer
.1 | Integrasi dengan system existing untuk mendapatkan data customer | Restu Ramdhika Wibowo, Samsu Rizal, Nurmansyah Candra Sakti |  | 2024-01-11 |  |  |  | 2024-02-01 | 21 | 0% | 16
-
-
Formulas:
WORK DAYS = IF(OR([END]=0,[START]=0)," - ",NETWORKDAYS([START],[END]))
END = IF(ISBLANK([START])," - ",IF([DAYS]=0,[START],[START]+[DAYS]-1))

## MOM 10-Januari-2024
MINUTE OF MEETING
| Date & Time | : 10 Januari 2024 Jam 11:30 s/d 12:00
| Location / Media | : Teams Meet
| Project | : CRM
| Agenda | : Meeting Kick Off
Participant
| KANMO | 1. Ibu Gita
2. Ibu Lita
| UIDESK | 3. Pak Restu
4. Pak Yoan
5. Pak Candra
6. Pak Rizal
Created by : Rizal
NO | TASK | DETAILS | STATUS | PIC
1 | Server | Server disediakan oleh Uidesk | Done | Uidesk (Pak Yoan)
2 | Meeting Online | Meeting berkala setiap 1 minggu sekali dihari rabu minimum 30 menit | Done | All
3 | Project Tracker | Uidesk membuatkan doc project tracker | Done | Uidesk (Rizal)
4 | Form Ticketing | Koreksi label dan susunan posisi di form transaksi ticketing | Done | Kanmo (Ibu Lita)

## MOM 17-Januari-2024
MINUTE OF MEETING
| Date & Time | : 17 Januari 2024 Jam 11:30 s/d 12:00
| Location / Media | : Teams Meet
| Project | : CRM
| Agenda | : Meeting Kick Off
Participant
| KANMO | 1. Ibu Gita
2. Ibu Lita
| UIDESK | 3. Pak Restu
4. Pak Yoan
5. Pak Candra
6. Pak Rizal
Created by : Rizal
NO | TASK | DETAILS | STATUS | PIC
1 | Nomor SIP Trunk SME | Akan diberikan Nomor SIP Trunk oleh Kanmo | On Progress | KANMO
2 | IVR & Flow | Sudah diberikan IVR sample dari kanmo ke uidesk menggunakan setting default jinggle | Done | KANMO
3 | Testing System EPIC & Ticketing |  | On Progress | UIDESK & KANMO
4 | Review Category Problem | Team Kanmo akan review category problem yang ada di aplikasi ticketing | On Progress | KANMO
5 | Team Kanmo akan check system ticketing langsung |  | On Progress | KANMO
6 | Integrasi dengan bantu dagang melalui order id |  | On Progress | UIDESK
7 | Dibuatkan iframe ke bantu dagang |  | Done | UIDESK
8 | Instalasi dan Testing EPIC pada laptop user KANMO | Dibutuhkan allow untuk user-user contact center untuk proses instalasi EPIC | Done | UIDESK & KANMO
9 | Integrasi Profiling Customer | Dibutuhkan koordinasi dengan team IT KANMO | On Progress | UIDESK & KANMO
10 | Deploy Modul Backend Email |  | On Progress | UIDESK
10 | Account Email Kanmo | Account email akan diberikan oleh Kanmo | On Progress | KANMO

## Email Kanmo
Brand | Link | User | Pass
Kanmo | Outlook | support@kanmogroup.com | Supp0rt@2019
Nespresso | Outlook | club.indonesia@nespresso.co.id | GoldenCoffee2018!
Havaianas | https://fs.alpargatas.com.br/adfs/ls/?RelayState=https%3A%2F%2Faccounts.google.com%2FCheckCookie%3Fcontinue%3Dhttps%253A%252F%252Fmail.google.com%252Fmail%252Fu%252F0%252F%26service%3Dmail%26osid%3D1%26ifkv%3DAU9NCcz8x8qXiteoBpIKeZfDJKN4XcdKmoUX_WX5WJGi3QLMcJ29AKKrytipt2sQBfONj5svaQThsw&SAMLRequest=fVJLT%2BMwEL4j7X%2BwfE%2FSZBepspqgLghRiUdEA4e9TZJJ6uLXepwW%2Fj1pClr2QK%2Bfv%2Fke41lcvGrFduhJWpPzNJ5xhqaxrTR9zp%2Bq62jOL4ofZwsCrZxYDmFjHvHvgBTYOGlITA85H7wRFkiSMKCRRGjEenl3K7J4Jpy3wTZWcba6yrnrtHvpO6ed62uF0G4QNdSu3qq2rmu7VRagV1vOnj9jZYdYK6IBV4YCmDBCsyyN0jTKzqvZXPzMxK%2F5H87KD6ff0hwbnIpVH0kkbqqqjMqHdTUJ7GSL%2Fn5k57y3tlcYN1Yf7EsgkrsR7kARcrYkQh%2FGgJfW0KDRr9HvZINPj7c534TgSCTJfr%2BP%2F8kkkIBy4HsIQAcgrn0CDfFiWrCYOvovmz3dAD4T8OK0xyL5Il98fOah4%2BqqtEo2b2yplN1feoQwFgx%2BGPtdW68hfJ8gjdMJkW3UTVQxGHLYyE5iy1lSHF3%2Fv5rxlt4B&client-request-id=2888e79f-c7c9-46a6-7005-0080000000e7 | alpa\indonesia | Alpa@2024Jan!

## Access Sytem
No | URL | Level | Access
1 | https://kanmo.uidesk.id/crm/ | Admin | user Admin : admin Password : Uidesk123!
2 |  | Agent Email | user Email : agentkanmoemail1 Password : Uidesk123!
3 |  | Agent Inbound | user Inbound : agentkanmoinbound1 Password : Uidesk123!
4 |  | Agent Social Media | user Social Media : agentkanmosocialmedia1 Password : Uidesk123!